## Annual Report.FN05.Apr-Sep.2012
Annual Report on NPA & SPERI Project in Si Ma Cai district, Lao Cai province (FN05)
(From April to December 2011)
No. | Activities | Outcomes | Indicators | Effective / impacts | Time | Participants / beneficiaries
Objective I: Stronger legal recognition on community right and local tradition governance over watershed community forest management
I.1 | Lobby local authorities for implementation of the joint-circurlar No.07/2011/TTLT-BTNMT&BNNPTNT on renting/leasing forest and allocating forestland for community
I.1.1. | Organized a meeting with the Lao cai provincial department of forestry on possibilities of cooperation related to community rights to forest land. | SPERI & the Lao cai provincial department of forestry agreed in a cooperation to carry out pilots on LFA to local communities in accordance with the joint-circular No.07. | Both sides set up a plan in carrying out a survey on forest management and possibility of the LFA to H'mong communities in Lung Sui and Nan San communes, Si Ma Cai district. | Head of Lao Cai provincial department of forestry understood values of community forest management, as well urgent need to (re) allocate and (re) map forest land for local communities to manage in long-run. | 15/7/2011 | 01 SPERI senior, 01 CODE senior and 04 representatives of Lao Cai provincial department of forestry.
I.1.2. | Conducted a survey on forestland management and right of H'mong communities over forestland in Lung Sui and Nan Sin communes, Si Ma Cai. | A matrix / mapping of forest owners (formal i.e. management board of protection forest and traditional i.e. H'mong communities, clans, groups of families and privates); analysis of overlapping over borders and governance bet. forestland holders; suggestions related to locations, scale and steps of LFA pilots implementation accordance with the joint circular No.07 in Lung Sui and Nan Sin. | A report of the survey shared with Si Ma Cai PC, relevant functional offices and Lao Cai provincial department of forestry. | Local authorities realized pratical situations, particularly overlaps and conflicts over forestland ownerships. | 23-29/7/2011 | 03 SPERI senior, 01 CODE expert and 5 representatives of Si Ma Cai Steering Committee on LFA incl. agriculture and rural development office, forest protection office
|  |  | A plan on organizing a workshop to develop roles/functions of SPERI, Lao Cai provincial department of forestry, Si Ma Cai district PC and functional offices, Lung Sui and Nan Sin communes, as well villages in carrying out pilots on LFA in line with the joint-circular No.07. | Advisory role of SPERI to the FLA program in Si Ma Cai / Lao Cai in regard with the joint-circular 07 was recognized by local authorities.
I.1.3. | Organized a workshop for an agreement of roles / functions of relevant stakeholders in carrying up pilots on LFA to local communities in line with the joint-cirucular No.07 in Lung Sui and Nan Sin communes, Si Ma Cai. | Stakeholders clearly defined functions and roles of each party in co-implementing pilots in line with the joint-circular No.07 in Si Ma Cai. | An MOU on cooperation of carrying out pilots on FLA to communities in line with the circurlar No.07 in Lung Sui and Nan Sin communes officially signed by SPERI/CODE, Si Ma Cai PC and Lao Cai provincial department of forestry. | Values of traditional forest governance of local communities (i.e. H'mong) is recognized by provincial and district authorities. | 2011-11-08 | 28 people representing Nan Sin & Lung Sui communes, Si Ma Cai healer network, Simacai PC, argiculture & rural development office, forest protection office, natural resource and environment office, magt board of watershed forest, district farmer uninon, Lao cai department of forestry, SPERI / CODE, students from FFS_Si Ma Cai.
|  |  | A detailed plan on carrying out pilots on LFA to communities in Ta Lung San village, Lung Sui commune was officially approved by Si Ma Cai PC. | Problems of local communities related to overlapping / conflicts over forest-land become concerns of provincial, district and communal authorities.
|  |  | Si Ma Cai Steering Committee on FLA which involves 8 members from different functional offices, vice chairman of the district (Mr. Nguyen Xuan Nhan) is head was established. | Advisory role of SPERI/CODE to the LFA in line with the joint-circular No.07 in Si Ma Cai, Lao Cai province was officially recognized.
|  |  | A technical team on FLA which involves 5 members from different functional offices, deputy office of forestry office (Mr. Nguyen Cong Tuong) is a team leader was set up. | Si Ma Cai PC contributed a part of finance and human resources in carrying out the two pilots.
A council of forestland allocation in Lung Sui was set up, which includes communal authorities, prestigious elders
I.1.4. | Lobby Si Ma Cai authorities to re-map and re-allocate forestland to local communities | Si Ma Cai authorities realized problems and potential challenges of the result and methods of mapping and forestland allocation implemented by the Si Ma Cai office of natural resources and environment in 2006. | Chairman of Si Ma Cai district PC issued a decision to cancel the results of mapping and forestland allocation in 2006. | Si Ma Cai authorities highly appriciated methods of community based FLA and asked SPERI to continue to advise re-mapping and re-allocating forestland to local communities. | Dec. 2011 | 5 seniors of SPERI and 1 expert of CODE, Si Ma Cai steering committee on FLA and Lung Sui council of land allocation.
A plan of re-allocating forestland to local communities from 2011 to 2015, which was set up based on the pilot in Lung Sui commune was approved by Si Ma Cai PC.
I.2. | Improve capacity of local communities on rights over land-forest via involving in FLA pilots
I.2.1 | Organized meetings with elders, healers, clan heads, key farmers and youths to identify overlapping of forestland. | 07 meetings were conducted with involvements of elders, healers, clan heads, key farmers, youths, forest officials and SPERI/CODE staffs; | 08 existing maps (around 1,000 ha) which reflect overlap of land border, forest governance in 8 communes were setup; 06 existing maps (around 500 ha) of overlap of land border and forest governance in 6 villages in Lung Sui were set up by healers and community traditional leaders. | Results of the survey were raised among local authorities and become guideline for FLA pilots in Lung Sui commune. | 10-28, Jul. 2011 | 73 people represent 8 communes in Si Ma Cai, 6 villages in Lung Sui commune, forest officials, students in FFS_Simacai and SPERI/CODE staffs.
Local stakeholders, esp. elders and youths are able to identify types of forestland overlaps via mapping traditional forests in compared with forests which were stated in the formal land-use maps.
I.2.2. | Provided practical training for members of herbal medicine and customary law network on skills of mapping. | 01 practical training was organized with participation of elders, healders, clan heads, key farmers, students and SPERI staffs. | Local participants are able to reading maps, identifying conflicts over forest-land between local communities and magt board of watershed forest. | Some participants are confident to use results of the meeting to raise and debate with local authorities in the workshop organized in 11/8/2011 (see activity No.I.1.3) | 10-12, Aug. 2011 | 21 key persons represent 4 communes in Si Ma Cai, students in FFS_Si Ma Cai and SPERI's staffs
I.2.3. | Organized consultations among loal authorities on govt. policies/laws on forest-land. | 01 consultation among Lao Cai provincial / Si Ma Cai authorities and technicians with Lung Sui commune authorities and villagers in Ta Lung Sui villag on govt. policies / law on forestland. | 05 communal authorities realized key relevant policies and law on forestland magt., use and development; they are able to organize and provide practical re-training for local villagers. | 05 communal authorities are confident and active in every stage of LFA, especially dealing with conflicts / overlapping of forest-land boundaries among stakeholders. | Aug-Sept-2011 | 11 Si Ma Cai district authorities and technicians, 03 FFS_Si Ma Cai students, 02 SPERI's staffs and 05 key Lung Sui communal authorities
05 communal authorities organized TOT on govt. policies for 60 villagers in Ta Lung Sui village.
I.2.4. | Organized training of trainers (TOT) for villagers on govt. policies/law on forestland. | 01 TOT on relevant govt. policies / laws on forest land was organized by 05 communcal authorities for villagers in Ta Lung Sui village | 40 key villagers in Ta Lung Sui village understood key relevant policies and law on forest land management, use and development; they are confident to apply these laws/policies in their practices. | Villagers are confident and active to involve in forest land survey, forest classification and solving conficts over overlaps on boundaries; they are confident to negotiate with other stakeholders in the process of re-mapping and re-allocating forestland. | Sept, 2011 | 60 villagers, 11 local authorities (provincial, district and commune), 02 SPERI's staffs.
I.2.5. | Provided advices on forestland survey and classification in the pilot in Ta Lung Sui village. | Villagers, Lung Sui and Si Ma Cai officials are confident to conduct forestland survey and classification in accordance with participatory and community based methods. | Areas and overlaps of forest land bet. different owners, esp. among community and govt. appointed magt. board of protection forest were recognized by whole related stakeholders. | Borders and areas of forestland traditional owners i.e. clans, 'thu ti' and 'no song' were officially recognized and approved. | Sept-Nov, 2011 | 60 villagers, 11 local authorities (provincial, district and commune), 02 SPERI's staffs.
|  |  | 05 types of forest land (312 ha) belonged to community (i.e. 'Thu Ti' and 'No Song' forests), clans, groups of families, families and govt. appointed magt. board of protection forest were re-classified via involvement of relevant stakeholders and the traditional forestland regime. | Si Ma Cai authority issued a decision to cancel the results of mapping and forestland allocation which were implemented by the Si Ma Cai office of natural resources and environment in 2006.
Conflicts among forestland owners, esp. bet. communities and govt. appointed magt. board of protection forest were settled.
I.2.6. | Provided advices on forest survey/ inventory and classification in the pilot in Ta Lung Sui village. | Villagers, Lung Sui and Si Ma Cai officials are confident to conduct forest/inventory and classification in accordance with participatory and community based methods. | 3 main types of forest (80 ha) i.e. traditional spiritual forest, protection forest, usage forest and production forest were classified. | Traditional spiritual forests i.e. 'Nao Long' and 'Thu Ti' which are being absent in the list of formal forest classification were recognized by provincial and district authorities. | Sept-Nov, 2011 | 60 villagers, 11 local authorities (provincial, district and commune), 02 SPERI's staffs.
|  |  | Status and bio-forest structure of different above forests were recorded. | Provincial and district authorities realized role and capability of local villagers / communities in managing forest resources in a sustainable way.
I.3. | Strengthen capacity of local partners in community based land forest allocation (CBLFA)
I.3.1. | Organized a training workshop on community based land forest allocation (CBLFA) | Participants, particularly district and provincial authorities, technicians (Lao Cai, Lang Son, Nghe An and Ha Tinh) identified types of land-forest overlapping (where, scale, causes and consequences); identified difficulties and solutions for CBLFA and forest magt; and agreed upon concepts and methods of CBLFA. | 01 guidelines with detailed steps on CBLFA in Lung Sui and Nan Sin communes was developed. | 01 detailed plan for carrying out pilots on FLA in Ta Lung San village, Lung Sui commune | 7-9/Sept/2011 | 55 people represent local communities, provincial and district authorities and functioning bodies (e.g. forestry, natural resources and environement, etc), researchers and media.
Several pilots (around 8,000 ha) on re-mapping and re-allocating forestland to communities are being implemented i.e. for Tay and Nung in Huu Lung district, Lang Son province, Black Thai in Que Phong district, Nghe an province, Co Tu in Quang Nam province and Ede in Kon Tum.
I.3.2. | Conducted field records on customary law of H'mong in forest-land governance | A week field records of customary laws and customary based institutions of Hmong in community forest governance was conducted. | Findings of the field records on customary law and customary based institutions on community forest governance are integrated into the guideline of FLA, esp. in terms of land boundary identification and conflict resolution. | Local authorities and technicians i.e. officers of Lao cai proncial department of forestry, district forestprotection office, office of natural resources and environment, govt. appointed magt. board of protection forests, etc., FFS Si Ma Cai students and local elders understand values of customary law and customary law-based institutions in forest protection. | Aug. 2011 | 11 local authorities and technicians, 03 FFS students, 02 SPERI's staffs and 10 key local villagers.
I.3.3. | Advised Si Ma Cai Steering Committee on FLA and Lung Sui Council of Land Allocation to analyse and report field records on forest land survey/classification. | Members of Si Ma Cai Steering Committee on FLA and Lung Sui Council of Land Allocation are able to analyse and make a report of the field records on forest land survey/classification. | A detailed report which reflects the current status of forest land use and magt.in the pilot was approved by Si Ma Cai functional authorities; A requested letter on cancel the results of mapping and land allocation in 2006 was set up and sent to Si Ma Cai PC. | Si Ma Cai PC approved the report and requested letter of the Si Ma Cai Steering Committee on FLA and Lung Sui Council of Land Allocation, and requested to re-mapping and re-allocating forestland to local communities. | 10 to 31 Dec. 2011 | 5 members of Si Ma Cai Steering Committee on FLA and 7 members of Lung Sui Council of Land Allocation and 3 SPERI seniors.
II. | Objective 2: Stronger network of key community leaders in forest governance and community health care
II.1. | Maintain and develop household/community herbal medicine gardens for the purpose of bio-diversity protection and community health care | Herbal medicine gardens in 11 communes such as Thao Chu Phin, Sin Cheng, Si Ma Cai, Man Than, Can Ho, Quan Than San, San Chai, Can Cau, Lung Sui, Lu Than, Nan Sin are being well protected by healers. | 21 herbal medicine gardens in which 19 gardens are managed by individual healers, 2 are managed by communities. | 1,362 types of herbal plants are being well protected for household / community uses to treat human illnesses and animal diseases. | Apr to Sept. 2011 | 48 healers of 11 communes in Si Ma Cai district
II.2. | Maintain / preserve herbal medicine & 'nao long' and 'thu ti' forests | Herbal medicine & 'Nao Long' and 'thu ti' forests in 5 communes (around 500 ha) such as Can Ho, Sin Cheng, Thao Chu Phin, Can Cau, San Chai are well protected by healers, clan heads and traditional community leaders via customary law and government law | 5 herbal medicine & 'nao long' and 'thu ti' forests with 350 types of herbal plants are strictly protected. | a) Regulations of herbal medicine preservation are being integrated into the customary law for 'nao long' and 'thu ti' forest magt. These regulation is recognized by communal and district [C; b) herbal & 'nao long' and 'thi ti' forests are now recognized by local authorities. These forests are being taken in to plan of Si Ma Cai district to alllocate to communities to manage in accordance with the circurlar No.07 | Apr to Sept. 2011 | 48 healers, 20 clan heads & traditional community leaders of 11 communes in Si Ma Cai district
II.3. | Provided practical training students in FFS_Si Ma Cai on using herbal plants in treating animal diseases / illness. | One practical training on using herbal medicines in treating animal diseases / illnesses for FFS Si Ma Cai students and staffs was organized. | 22 remedies from using 50 herbal plants for preventing and treating animal diseases/inllness are introduced and trained. | Students are able to apply knowledge / experiences learnt from healers into practices (e.g.FFS_Si Ma Cai and their home). Sutdents could treat normal illness of domestic animals by herbal medicines. | 16-17, Jun. 2011 | 23 students in FFS_Si Ma Cai and 05 SPERI staffs
II.4. | Maintain and develop Si Ma Cai network of herbal medicine
II.4.1. | Monthly meeting among the network's members within 13 communes for sharing knowledge | Values of voluntary, sharing/helping and structure of the network are being promoted. Total members of the network are 47, with 4 people are members of the network's coordinating board. | 9 meetings were organized rotatedly in 9 communies with participation of 47 members. | 40 patients and 12 buffaloes, 20 pigs were sucessfully treated by the network's members within 9 months. | Apr to Sept, 2011 | 47 healers in each meeting.
II.4.2 | Participated in the workshop on Community based FLA in Lang Son province (organized by CIRUM) | 02 people participated in the workshop for 2 days. | Participants learned experiences from the workshop in terms of challenges for forest magt. and approaches of community based FLA. | Lessons learnt from the workshop are being applied into the LFA as mentioned in the objective I. | 4-5 May. 2011 | 2 people - 1 elder representing for the Simacai's herbal network and 1 youth
II.5. | Organized an inter-provinces forum on community forest towards community rights to forestland. | Experiences in community forest governance were shared openly among participants. | SWOT of community forests in context of market economy and govt. policies, esp. the recent issurance of the joint-circular 07 was identified by participants. | Participants set up a plan to strengthen existing community forests (appropximately 15,000 ha), as well lobby local authorities to allocate these forests for local communities. | 23-24, Dec. 2011 | 40 partipants representing community forests of Ha Nhi, H'mong in Lao Cai, Tay and Nung in Lang Son, Black Thai in Nghe An, Kinh in Ha Tinh, SPERI, CIRUM and CODE.
Objective III: Stronger network of capable and confident indigenous youths in eco-farming
III.1 | In collaboration with Lao Cai Provincial Vocational Training to provide two years training course in veterinary for indigenous youths
III.1.1 | Organized the semester II (basic knowledge / skills in animal husbandry and veterinary) for 23 students in FFS_Si Ma Cai | 05 subjects were completed including herbal medicines in animal husbandry and veterinary, medical veterinary, animal husbandry and disease prevention, animal surgery, composting, nursery and action research / experimental. | 02 distinctions, 06 credit and 15 passed | Vocational Training Center of Si Ma Cai district asked SPERI for application training methods of FFS_Si Ma Cai and cooperation in providing short-courses for farmers. | Jan-Jun 2011 | 23 students, 05 SPERI's staffs, simacai technicians and teachers of Lao Cai vocational training
III.2. | Organize the semester III (advanced knowledge / skills in animal husbandry and veterinary) for 23 students in FFS_ Si Ma Cai | 10 training subjects including basic micro-organism, animal disease prevention and treatment, cropping, meat inspection, advanced IT, chickent raising, food safety and hygiene, group working, nursery, organic vegetable were completed. | Students are confident to apply these knowledge into practice. Especially, these knowledge are foundation in which students could apply into specialized subjects in the second year. | 06 students got awards from Lao Cai Vocational Training for their efforts in learning and practicing | Jul-Dec, 2011 | 23 students, teachers of Lao Cai vocational training, SPERI's staffs and Si Ma Cai technicians
III.3. | Provided practical training on eco-farming (e.g. composting, water & waste mangt, farming design, etc) for key farmers and authorities / technicians of Dai Tu district, Thai Nguyen Province where are project sites of Church World Service in Vietnam (CWS) | Participants realized values of eco-farming as well are able to practice skills shared by FFS_Si Ma Cai staffs. | Participants applied lessons learnt from the training i.e. waste and grey water magt, composting into their localities. | CWS wants to study more the methods of FFS's operation for its projects. | 3-5 Apr, 2011 | 28 key farmers and authorities of Dai Tu district, Thai Nguyen province, 23 students and 4 FFS_Si Ma Cai staffs
III.4. | Provided pratical training on composting, mulching, bio-gardening, canomy pruning for farmers in Si Ma Cai | 50 farmers - students of the Si Ma Cai Vocational Training Center attended four times (1 day / time) study tour and training at FFS_Si Ma Cai. | Farmers understood values of eco-gardening. They are confident to practice some basic skills in eco-gardening i.e. composting, mulchiing, canopy prunning, etc. | The Si Ma Cai Vocational Training Center asked for long-term cooperation with FFS_Si Ma Cai to organize short and long-term training courses for farmers. | Apr-Sept, 2011 | 50 farmers - students in Si Ma Cai and staffs of FFS_Si Ma Cai / SPERI
III.5. | Provided practical training for interns of Thailand Volunteering Service (TVS) on eco-farming, landscape design, fruit tree magt. and FFS approach. | An informal sharing information forum bet. interns and FFS Si Ma Cai students, SPERI staffs and Si Ma Cai eco-farming was set up. | Interns planned to go back FFS Si Ma Cai for further studies. | Interns become bridge builder / connectors focr SPERI to connect with eco-farming and ffs network in Cambodia (i.e. CEDAC) and Myanmar (i.e. METTA). | Nov-Dec. 2011 | 03 interns from Thailand, Cambodia and Myanmar, Si Ma Cai Eco-farming network, 23 FFS Si Ma Cai students and 04 SPERI staffs.
III.6. | Upgraded infrastructures and facilities for training in FFS_Si Ma Cai | 01 eco-kitchen, 01 eating place, repairing a roof of the community / training house, moving a living house of student. | Eco-kitchen and eating place are able to serve 40 people regularly; the living house could serve 23 students; students now have a safe and stable place for their living and studies. | Lao Cai People's Committee asked for Lao Cai Vocational Traning to study FFS's methods / approaches in order to expand this model in other districts in Lao Cai province. | Aug-Sept, 2011 | Staffs of FFS_Simacai / SPERI with involvement of 23 students
|  | 02 laptops and 01 camera were equipped. | These facilities are being effectively used by SPERI's staffs in Si Ma Cai. | Knowledge, skills and pictures from Si Ma Cai region are being oftent shared with all staffs in SPERI and students in network of FFSs. | July - Aug, 2011 | Staffs of FFS_Simacai / SPERI
III.7. | Set up training models/ experimentals for students to study | 04 training models (growing peanut and winter corn, chicken and black pig raising) which combine experimental and production are being conducted by groups of student. | Knowledge and skills from models are being collected and analysed by students to develop curriculum for further researches and teaching. | Students are able to connect knowledge from experimentals to different micro geo-climate conditions in their villages; models become live curriculum for students, farmers and practictioners to learnt and share experiences. | Aug-Dec, 2011 | FFS's Si Ma Cai staffs and 23 students